## Sheet1
Task List
| Hardware | Predecessor | Difficulty (/10)
1 | Build Arm | None | 5
2 | Purchase Servos | None | 1
3 | Purchase EEG cap & electrodes | None | 3
4 | Design additional amplifiers and filters | 3 | 5
5 | Control Servos using software | 2 | 1
6 | Refine (PCBs, cables, batteries) | 1 - 5 | 5
Software
7 | Write 5 channel PWM functions | None | 5
8 | Write ADC access functions. Maybe use DMA and double buffer with RTOS? | None | 7
9 | MATLAB STFT on published EEG data | None | 3
10 | MATLAB SVM Classification of published EEG data | 17 | 5
11 | Embedded C STFT on streamed published data? | None | 8
12 | Embedded C SVM Classification of published data? | 17 | 9
13 | Embedded C STFT on realtime EEG data | 4, 11 | 10
14 | Embedded C SVM Classification of realtime EEG data | 4, 11, 17 | 10
15 | Control System design | 14 | 5
16 | Serial / App / Websocket control? | ? | 5 - 10
Documentation
17 | AAR vs SVM | None | 4
18 | What we're looking for in the EEG, why use FFT | None | 4
19 | Why are we doing this? Will people use a BCI prosthetic? | None | 2
20 | Benefits | None | 2